Forerunners Organization – Product Roadmap (2026–2029)

This repository hosts Forerunners' product roadmap, milestones, and M&E framework for 2026–2029. It supports planning, donor reporting, and team alignment across youth, women, and community programs in Myanmar.

Product Lines

- P1: Life Skills & Leadership

- P2: Livelihoods & Green Micro‑Enterprise

- P3: Digital Literacy & Safety

- P4: Mental Well‑being & Resilience

- P5: Community Inclusion & Partnerships

- P6: Digital M&E + Knowledge System

Quick Links

- Download full roadmap (Excel)

- View roadmap table (Markdown)

- M&E Framework & Indicators

Roadmap Overview

| Year | Focus | Key Milestones |
| --- | --- | --- |
| 2026 | Foundation | Curriculum v1 approved (Q2 2026); M&E framework + baseline (Q3 2026) |
| 2027 | Scale & Integrate | 1,000 graduates; Dashboard v1 (Q1 2027); First impact brief (Q4 2027) |
| 2028 | Deepen & Diversify | Alumni mentor network live; 40% green practice adoption |
| 2029 | Consolidate & Sustain | Finance partnership signed; 3 community-led components |

How We Work

- Community‑based, training + coaching model (learning by doing)

- Participatory engagement with local stakeholders

- Integration of digital tools and green practices

- Adaptive management to Myanmar's changing context

Getting Involved

- Team members: Open issues for updates, risks, and decisions.

- Partners: Use templates to align cohort plans and milestone logs.

- Donors: See one‑pager templates and impact briefs (coming 2027).

License & Use

Content is shared for learning and collaboration. Please credit Forerunners Organization when adapting materials.