M&E Framework & Indicators

Overview

This framework defines the key indicators Forerunners will track from 2026–2029 to measure outputs, outcomes, and impact across all product lines.

Indicator Types

Output Indicators

Track what we deliver (activities and direct products).

| Indicator Name | Definition | Data Source |
| --- | --- | --- |
| Participants trained | Total unique participants completing any Forerunners training | Training attendance sheets |
| Cohorts completed | Number of cohorts that finished the full curriculum | Cohort completion logs |
| Mentors trained | Number of peer mentors/facilitators trained | Trainer records |

Outcome Indicators

Track changes in knowledge, behavior, and conditions.

| Indicator Name | Definition | Data Source |
| --- | --- | --- |
| Confidence increase | Share reporting higher confidence/decision-making post-training | Pre/post surveys |
| Income diversification | Share with 2+ income sources post-program | Follow-up surveys |
| Green practice adoption | Share of enterprises using at least one green practice | Business checklists |
| Digital use for business/learning | Share using digital tools for income or learning | Usage logs/surveys |
| Well-being improvement | Share with improved well-being scores | Well-being scales |

Impact Indicators

Track long-term change in communities.

| Indicator Name | Definition | Data Source |
| --- | --- | --- |
| Household income stability | Share reporting stable or rising household income | Annual review |
| Youth/women leadership roles | Number in formal community leadership roles | Community records |
| Green enterprise survival | Share of green enterprises operating 12+ months | Business registry |
| Digitally active community networks | Number of active digital groups/channels | Platform analytics |

Targets (2027–2029)

| Indicator | 2027 | 2028 | 2029 |
| --- | --- | --- | --- |
| Participants trained | 3,000 | 6,000 | 9,000 |
| Cohorts completed | 20 | 40 | 60 |
| Mentors trained | 60 | 120 | 180 |
| Confidence increase | 60% | 70% | 75% |
| Income diversification | 35% | 45% | 55% |
| Green practice adoption | 25% | 40% | 50% |
| Digital use for business/learning | 40% | 55% | 65% |
| Well-being improvement | 50% | 60% | 65% |
| Household income stability | 55% | 65% | 70% |
| Youth/women leadership roles | 80 | 150 | 220 |
| Green enterprise survival | 60% | 70% | 75% |
| Digitally active community networks | 20 | 40 | 60 |

Data Collection Routine

- Pre/post tests: At start and end of each cohort

- Monthly cohort logs: Track attendance, sessions, outputs

- Quarterly reviews: Analyze trends, adapt programming

- Annual impact brief: Summarize yearly progress for donors

Data Protection

- Obtain informed consent before collecting personal data

- Collect minimum necessary data

- Store data securely with access controls

- Anonymize data for public reporting