Roadmap Table (2026–2029)

| Product | 2026 (Foundation) — Outcomes & Outputs | 2027 (Scale & Integrate) — Outcomes & Outputs | 2028 (Deepen & Diversify) — Outcomes & Outputs | 2029 (Consolidate & Sustain) — Outcomes & Outputs | Key Milestones (all years) |
| --- | --- | --- | --- | --- | --- |
| P1 Life Skills & Leadership | Outcome: Improved confidence, decision-making, and civic participation among youth/women. Outputs: 6–8 cohorts; facilitator guides; peer circles. | Outcome: Stronger youth/women leadership in communities. Outputs: 12+ cohorts; leadership labs; community projects. | Outcome: Sustained peer leadership and mentoring. Outputs: Advanced modules; alumni mentors; local leadership councils. | Outcome: Community-led leadership systems. Outputs: Handover playbooks; local facilitator certification. | M1: Curriculum v1 approved (Q2 2026). M2: 1,000 graduates by end-2027. M3: Alumni mentor network live (2028). |
| P2 Livelihoods & Green Micro-Enterprise | Outcome: Initial income-generating and green activities started. Outputs: Bootcamps; starter kits; green micro-grant pilot. | Outcome: Diversified, more stable livelihoods. Outputs: SME coaching; market linkage days; green enterprise pipeline. | Outcome: Eco-friendly enterprises scaling. Outputs: Advanced green tracks; supplier linkages; impact stories. | Outcome: Resilient green livelihoods institutionalized. Outputs: Revolving fund/finance partner; local business hubs. | M1: 100 micro-enterprises launched (2027). M2: 40% adopt green practices (2028). M3: Finance partnership signed (2029). |
| P3 Digital Literacy & Safety | Outcome: Foundational digital competence and safety awareness. Outputs: Basic/advanced courses; safety protocols; device access pilots. | Outcome: Expanded digital engagement for education/business. Outputs: Online entrepreneurship module; trainer pool; low-bandwidth resources. | Outcome: Digital income pathways growing. Outputs: Digital marketing labs; e-commerce pilots; cybersecurity refreshers. | Outcome: Digitally connected communities. Outputs: Community device-sharing scheme; certified digital trainers. | M1: 1,500 digitally trained (2027). M2: 300 online sellers active (2028). M3: Device-sharing live (2029). |
| P4 Mental Well-being & Resilience | Outcome: Increased awareness and help-seeking. Outputs: Awareness sessions; support groups; referral map. | Outcome: Improved emotional resilience and coping. Outputs: Resilience coaching; facilitator training; partner MOUs. | Outcome: Stronger community support ecosystems. Outputs: Peer supporter network; periodic group sessions; case management lite. | Outcome: Embedded well-being practices. Outputs: Community champions; sustained referral pathways; learning briefs. | M1: Referral pathway formalized (2026). M2: 50 peer supporters trained (2028). M3: Annual well-being report (2029). |
| P5 Community Inclusion & Partnerships | Outcome: Greater participation and inclusion in activities. Outputs: Mobilization events; inclusion guidelines; partner mapping. | Outcome: Strengthened local networks and co-design. Outputs: Community advisory groups; participatory planning cycles. | Outcome: Inclusive decision-making normalized. Outputs: Local partnership MOUs; joint initiatives. | Outcome: Community-led governance of select components. Outputs: Handover frameworks; local stewardship committees. | M1: Stakeholder matrix live (2026). M2: 10 active local partners (2028). M3: 3 community-led components (2029). |
| P6 Digital M&E + Knowledge | Outcome: Evidence-based decisions and donor reporting. Outputs: Indicator framework; simple digital database; baseline. | Outcome: Timely, credible data for learning and donors. Outputs: Dashboards; quarterly reviews; first impact brief. | Outcome: Continuous improvement cycle. Outputs: Case study library; donor-ready reports; adaptation logs. | Outcome: Sustainable knowledge system. Outputs: Playbooks; open templates; next-strategy inputs. | M1: M&E framework + baseline (Q3 2026). M2: Dashboard v1 (Q1 2027). M3: First impact brief (Q4 2027). |